## MM Launch Timeline Template
Mise Mode™ Food Launch Timeline
Item | Completion Target Date | Calendar Date | Team Responsible | Task Status | Completed Date
Internal Food Team "FT" R&D Completed | 13 weeks out | 2023-11-15 | FT, Purchasing |  |  | Directions: Once your annual development calendar is filled out and solidified, its time to customize this project management launch tool.
recipes, selection, cost, price, nutritionals, packaging
Food Meeting completed - Price, Selection, Nutritionals confirmed | 12 weeks out | 2023-11-22 | FT, Communications, Purchasing
Marketing Meeting to Review Line of Approved Items | 11 weeks out | 2023-11-29 | FT, Marketing Communications |  |  | **If you are a single operator and don't have teams that support all of these areas, identify the people who can help you manage these launches in each critical area. And if it's just you - don't sweat it - this tool will help you stay on track and organized and keep the launch process seamless.
price, selection and nutritionals reviewed
initial language and supplemental material discussion
Purchasing Meeting | 11 weeks out | 2023-11-29 | FT, Purchasing
Anticipated product volume discussed
Any other items reviewed
Food & OPS Mtg | 10 weeks out | 2023-12-06 | FT, Operations, Purchasing |  |  | 1. Review this tab and read through Column A tasks and deliverables that get you to Launch.
New equipment, review of items, range etc…
Shelf Life Tests Complete (To Go Items) | 10 weeks out | 2023-12-06 | FT
1st Draft Training Materials Complete | 10 weeks out | 2023-12-06 | FT |  |  | 2. Go to the second tab "YOUR Launch Timeline" and start to customize this tool for your business.
Recipes (Internal)
Recipe Cards (training)
Baking & Reheating Guides
Job Aides - supporting Operations Training Materials
Batch Testing
Kitchen Tools for Accurate Portioning Identified | [5 empty] | Tip: This is a living, breathing timeline that is meant to be updated as you learn more about what steps you need to ensure a smooth launch. Get really detailed with this, and you can delegate the management of this process to a trusted team member. If you invest in making this tool reflect exactly what's needed at every step of the way, your launches will be smooth every time.
Shelf Life & Storage Guides Updated
Menu Category Organizer Updated
Team Overall Training Points Drafted
Meeting - IT / Food Team | 9 weeks out | 2023-12-13 | FT, IT
Discuss launch & Place Costing in Software Program (back end)
POS Changes / Updates Mapped Out
Final Recipes confirmed & shelf life trials and testing complete | 8 weeks out | 2023-12-20 | FT
If you need more support, want a Custom Menu MGMT tool that includes your Recipes, COGS and Labor, or anything else you need help with, contact us at orderup@essayerfoodconsulting.com. We've got you!
Purchasing Mtg | 8 weeks out | 2023-12-20 | FT, Purchasing
agreement on pack size & review of all products (shelf life)
any outstanding items solidified at this point
projections reviewed and confirmed
Final Sales Price Confirmed for all items | 7 weeks out | 2023-12-27 | Communicatons, FT, Purchasing
All Department Meeting for Updates / Progress Report | 7 weeks out | 2023-12-27 | FT, IT, Purch, Mktg, Ops
Final Nutritional Info Confirmed | 7 weeks out | 2023-12-27 | FT
Nutritional Guides Updated
Marketing / IT Meeting - Website | 6-7 weeks out | 2023-12-27 | Mktg, IT, FT
Review of nutritonal info, internal data input to backend system
Final Ingredient & Equipment Pricing Confirmed | 6 weeks out | 2024-01-03 | Purchasing
Product & Ingredient De-List Changes identified and confirmed | 5-6 weeks out | 2024-01-03 | FT, Purchasing
Final Training Materials Due (Job Aides, etc…) | 5 weeks out | 2024-01-10 | FT
Recipe Execution Testing - Ops Kitchen Trial | 5 weeks out | 2024-01-10 | Operations, FT
Ingredient Prep List Mtg - Discuss & Draft | 5 weeks out | 2024-01-10 | FT
Map Out OPS Training Days | 5 weeks out | 2024-01-10 | Operations, FT
Marketing Meeting - Final Review | 4 weeks out | 2024-01-17 | Mktg, Comm, FT
Rough draft language - fine tuning etc…
Review all signage and labels needed (price tags, etc…)
Any Batch Recipes from Vendors Tested & Approved | 3-4 weeks out | 2024-01-17 | Purch, FT
Training Team Discussion | 3-4 weeks out | 2024-01-17 | Training, FT
Team Training Points Due to Ops | 3 weeks out | 2024-01-24 | FT
Restaurant Set Up / Grab N Go Placement Plans Finalized | 3 weeks out | 2024-01-24 | Operations, FT
Stock & PARS Control Sheet Draft | 3 weeks out | 2024-01-24 | Purchasing, OPS, FT, IT
Recipes, pack sizes and ingredient info
OPS Presentation (include discussion on launch specific focus for checklist) | 3 weeks out | 2024-01-24 | OPS, Mktg, FT
Store Communication Due in Team member Newsletter | 3 weeks out | 2024-01-24 | FT, OPS
Products to Delist and Run Down in Inventory etc…
Blank for you to fill in | 3 weeks out | 2024-01-24 | FT
Training Materials Printed and Laminated | 3 weeks out | 2024-01-24 | FT, OPS
Marketing Materials Printed and Ready for Distribution | 2 weeks out | 2024-01-31 | Mktg
OPS Training Days | 2 weeks out | 2024-01-31 | OPS, FT, Mktg, Comms
Small groups - training sign off for all stores
Coordinate Training Material Delivery and Ingredients for Recipe Execution
IT Meeting | 1 week out | 2024-02-07 | IT, FT, OPS
Final review before LIVE rollout
All associated tasks for new products & de-list in place & ready
POS Updates Ready to Go
Go live | LIVE | 2024-02-14 | All

## YOUR Launch Timeline
Mise Mode™ Food Launch Timeline
Item | Completion Target Date | Calendar Date | Team Responsible | Task Status | Completed Date
STEPS:
Internal Food Team "FT" R&D Completed | 13 weeks out | -91 | FT, Purchasing |  |  | 1. Add YOUR Go LIVE date in Cell C103, and all the other dates will populate on the timeline.
recipes, selection, cost, price, nutritionals, packaging
2. Update your to-do Items in Column A
Food Meeting completed - Price, Selection, Nutritionals confirmed | 12 weeks out | -84 | FT, Communications, Purchasing
3. Update Column E using a Traffic Light system. Red, Yellow & Green for Status
Marketing Meeting to Review Line of Approved Items | 11 weeks out | -77 | FT, Marketing Communications
price, selection and nutritionals reviewed | [5 empty] | 4. Keep Notes here - and be detailed. The more you capture, the easier the process is to manage!
initial language and supplemental material discussion
Purchasing Meeting | 11 weeks out | -77 | FT, Purchasing
Anticipated product volume discussed
Any other items reviewed
Food & OPS Mtg | 10 weeks out | -70 | FT, Operations, Purchasing
New equipment, review of items, range etc…
Shelf Life Tests Complete (To Go Items) | 10 weeks out | -70 | FT
1st Draft Training Materials Complete | 10 weeks out | -70 | FT
Recipes (Internal)
Recipe Cards (training)
Baking & Reheating Guides
Job Aides - supporting Operations Training Materials
Batch Testing
Kitchen Tools for Accurate Portioning Identified
Shelf Life & Storage Guides Updated
Menu Category Organizer Updated
Team Overall Training Points Drafted
Meeting - IT / Food Team | 9 weeks out | -63 | FT, IT
Discuss launch & Place Costing in Software Program (back end)
POS Changes / Updates Mapped Out
Final Recipes confirmed & shelf life trials and testing complete | 8 weeks out | -56 | FT
Purchasing Mtg | 8 weeks out | -56 | FT, Purchasing
agreement on pack size & review of all products (shelf life)
any outstanding items solidified at this point
projections reviewed and confirmed
Final Sales Price Confirmed for all items | 7 weeks out | -49 | Communicatons, FT, Purchasing
All Department Meeting for Updates / Progress Report | 7 weeks out | -49 | FT, IT, Purch, Mktg, Ops
Final Nutritional Info Confirmed | 7 weeks out | -49 | FT
Nutritional Guides Updated
Marketing / IT Meeting - Website | 6-7 weeks out | -49 | Mktg, IT, FT
Review of nutritonal info, internal data input to backend system
Final Ingredient & Equipment Pricing Confirmed | 6 weeks out | -42 | Purchasing
Product & Ingredient De-List Changes identified and confirmed | 5-6 weeks out | -42 | FT, Purchasing
Final Training Materials Due (Job Aides, etc…) | 5 weeks out | -35 | FT
Recipe Execution Testing - Ops Kitchen Trial | 5 weeks out | -35 | Operations, FT
Ingredient Prep List Mtg - Discuss & Draft | 5 weeks out | -35 | FT
Map Out OPS Training Days | 5 weeks out | -35 | Operations, FT
Marketing Meeting - Final Review | 4 weeks out | -28 | Mktg, Comm, FT
Rough draft language - fine tuning etc…
Review all signage and labels needed (price tags, etc…)
Any Batch Recipes from Vendors Tested & Approved | 3-4 weeks out | -28 | Purch, FT
Training Team Discussion | 3-4 weeks out | -28 | Training, FT
Team Training Points Due to Ops | 3 weeks out | -21 | FT
Restaurant Set Up / Grab N Go Placement Plans Finalized | 3 weeks out | -21 | Operations, FT
Stock & PARS Control Sheet Draft | 3 weeks out | -21 | Purchasing, OPS, FT, IT
Recipes, pack sizes and ingredient info
OPS Presentation (include discussion on launch specific focus for checklist) | 3 weeks out | -21 | OPS, Mktg, FT
Store Communication Due in Team member Newsletter | 3 weeks out | -21 | FT, OPS
Products to Delist and Run Down in Inventory etc…
Blank for you to fill in | 3 weeks out | -21 | FT
Training Materials Printed and Laminated | 3 weeks out | -21 | FT, OPS
Marketing Materials Printed and Ready for Distribution | 2 weeks out | -14 | Mktg
OPS Training Days | 2 weeks out | -14 | OPS, FT, Mktg, Comms
Small groups - training sign off for all stores
Coordinate Training Material Delivery and Ingredients for Recipe Execution
IT Meeting | 1 week out | -7 | IT, FT, OPS
Final review before LIVE rollout
All associated tasks for new products & de-list in place & ready
POS Updates Ready to Go
Go live | LIVE |  | All